## Sheet1
Date Planned | Expected Start Date | Date Achieved | Work Planned | Work Achieved | Next Steps | Notes, challenges, special info
2020-01-20 | 2020-01-20 | 2020-01-20 | Module intro lecture | stayed awake all the way through
| 2020-01-22 | 2020-01-22 | Download Data | Data files downloaded
| 2020-01-22 | 2020-01-30 | Open and explore data file | Opened data files, imported to array | Plot and explore data | Struggled with opening NetCDF files, had to download library
| 2020-01-23 | 2020-01-25 | Outline project plan | Thought of an idea, made notes | check with teaching staff, turn into project spec | Delayed by difficulty opening NetCDF files
2020-01-27 | 2020-01-27 | 2020-01-27 | Specification lecture. | Most fun ever! I LOVE this module!
| 2020-01-29 | 2020-01-30 | Turn project outline into SMART list. | Few SMART points created. |  | Not all project details easy to define in a measurable way.
| 2020-01-31 | 2020-01-31 | Fill out rest of spec document template. | Wrote most of the specification template: introduction, risks and assumptions, out of scope things, project management. | Finish the rest of the specifications and formalise it. | Info complete, continue rest of project and finalise the formal text later on.
2020-02-05 | 2020-02-07 | 2020-02-07 | Code planning lecture.
| 2020-02-09 | 2020-02-09 | Create a pseudo-code of the program. | Created a pseudo-code . | Follow the pseudo-code and implement it in Matlab. | Hard to predict what functions are going to be used.
| 2020-02-10 | 2020-02-10 | Implement first features of the program | Implemented the main function of the program for reading, compiling and plotting data on the map | Follow the flowchart.
2020-02-12 | 2020-02-14 | 2020-02-14 | Formalise specifications document text | Formalised the specifications document and added new explanation about the project, added SMART targets, included acronyms and term.
2020-02-19 | 2020-02-21 | 2020-02-21 | Find articles that are corelated with the project and include them into the specifications document. | Found three articles which are corelated and read them. | Reference the articles in an appropriate way.
| 2020-02-21 | 2020-02-21 | Continue on implementing the program with new features | Implemented the GUI for the program with colourblind functionality and iteration through maps functionality.
Tested functionalities of the code, by giving different input than expected and fixed issues with different inputs (when there is 25 files but file that is read is 26 or 0 and so on)
2020-02-26 | 2020-02-28 | 2020-02-28 | Complete the rest of the program and comment the code. | Completed the rest of the program and commented everything properly + referenced not my parts code. | Do not add new features to do not crash or mess up the program. Add appropriate references in some parts of the code.
| 2020-02-28 | 2020-02-28 | Continue on testing the program | Continued on testing the program. Using different functionalities of GUI to see when the code might crash and fixing those issues.
2020-03-02 | 2020-03-04 | 2020-03-15 | Fix issues bug that may occur while running the program | Tested the program and fixed bugst and issues that were found in the new version of the program. | Start writing the report for the project | The project has been delaying on fixing the issues that the program had. The reason for this is because there were a lot of things to fix and most importantly a lot of changes needed to be made to the code itself so research has been done throughout these days
| 2020-03-04 | 2020-03-15 | Continue on commenting the program | The program has been fully commented
2020-03-09 | 2020-03-31 | 2020-04-04 | Start writing the report for the project and write half of it. | Written two sections of the report. | The rest of the report must be completed in between 2 weeks.
| 31/04/2020 | 2020-04-04 | Modify the specification document | Specification document has been modified and some things have been changed whereas some of them were added
2020-04-01 | 2020-04-10 | 2020-04-10 | Write the rest of the report for the project. | The full report has been written and modified so it would be in a pleasing format. | Start working on the viva presentation of the project.
| 2020-04-10 | 2020-04-10 | Post the program on GitHub. | The program has been submitted on GitHub
2020-04-11 | 2020-04-13 | 2020-04-13 | Create a viva presentation for the project using Screen O Matic software. | The viva presentation was created and all of the questions were answered in an appropriate way. |  | Some of the questions were misleading and confusing, so the way it was answered might be incorrect.
| 2020-04-13 | 2020-04-13 | Complete writing the specification document and report | Both of the documents were completed and no further changes will be made
2020-04-15 | 2020-04-21 | 2020-04-21 | Complete a viva video presentation | Completed the viva presentation
| 2020-04-21 | 2020-04-21 | Finish the project | Project has been submitted